## Sheet1
ETA for Wed Jobs API's
Sr. No. | Module | Status | Submodule | Time
1 | Common | Done(SMS Gateway integration pending) | Login,signup,reset password,change password for user and employer, SMS gateway integration | 1.5 Day
2 | Company User Journey | Done | a.Verification after registration | 2 Day
|  | Done | b.The company can activate and deactivate the opening
|  | Done | c.Create a Project - For a Company(CRUD)
|  | Done | d.Job(CRUD)
|  | Done | e. Jobs List
|  | Done | f. Duplicate the Job with other minor factors
3 | User journey |  | API 's for user module e.g. like,comment,apply,jobs listing as per filters and other flow aspects | 4 Day
4 | Admin Panel with role wise | Done | API's for role wise as per documentation | 4 Day
|  | Done | User/Company Management(CRUD for both)
|  | Done | Analytics (Data Points need to be defined prior to the development).
|  | Done | Blog Management
|  | Done | Approval panel
|  | Not Done | SEO Management
|  | Done | Header and Footer script management and related API's
5 | Payment Gateway and Notification related API's |  | Webhook,payments,web notification etc. | 3 Day